|  |  |  |  |
| --- | --- | --- | --- |
| **Tasks** | **Duration**  **(Days)** | **predecessors** | **Lead/lags** |
| **Management & Finance** | 15 Days | - |  |
| **Development** | 45 Days | Management & Finance | Lag 5 Days |
| **Marketing** | 35 Days | Management & Finance / Development | Lead 20 Days |
| **Public Relation** | 20 Days | Management & Finance / Development / **Marketing** | Lead 10 Days |

**Assuming The relation between all of the tasks is Finish to start (FS):**